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	27.12.2023.
	Nr. 2.5/2023/5139

	Uz 
	Nr. 


 
	
To the tenderers of the negotiated
procedure No. AST2023/149-ES




Subject: Negotiation procedure No. AST2023/29 - answers to the candidate's requests for clarifications
Herewith we provide answers to the tenderers' requests for clarifications regarding the negotiation procedures regulations No. AST2023/149-ES " Supply of 110/21/10.5 kV 25 MVA transformer to the substation "TEC-2"":

Tenderer's request for clarification No.1:
With reference to subject project, we kindly ask you to postpone the Tender submission date by 31.01.2024, if possible. Extension is required due to temporary overload of our engineering department as well as forthcoming holidays season and actual closure of the factory from 22nd of December, 2023 till 3rd of January, 2024.

Clarification No.1
The deadline for submitting of tenders will not be extended.

Tenderer's request for clarification No.2:
In annex 1 you mention following, - We will ensure the possibility to carry out inspections of the delivery of the Goods and performance of production tests in the presence of the Customer's representatives at the manufacturer's factory at least three working days before the Goods are shipped from the manufacturing plant. At least ten working days before sending the goods from the manufacturer's factory, we will inform the Customer's representative about the period during which it is possible to inspect the goods.
Please confirm that by performance of production tests you mean factory acceptance tests. If you meant something else please explain

Clarification No.2
We confirm that we mean the plant's acceptance tests. The tests are specified in the technical specification for the transformer. 

Tenderer's request for clarification No.3:
In tender regulations at point 16.2. it mentioned following, Tenders will be checked for arithmetical errors. Errors will be corrected according to the rules of arithmetic. Please explain what you meant by arithmetical errors.

Clarification No.3
During evaluation of tenders the public service provider shall verify whether there are arithmetical errors in the tender. If such mistakes are established, the public service provider shall correct them. The public service provider shall inform the tenderer whose errors have been corrected of the correction of errors and the corrected sum of the tender. Upon evaluating a financial tender, the public service provider shall take into account corrections.
If the sum of the indicated units' prices will be different with the indicated total sum, we will recalculate the total sum: A+B=C. 

Tenderer's request for clarification No.4:
In Annex3, time schedule of documentation for approval stated as 60 days after signing of contract. For comprehensive documentation 2 months is not enough. Here we kindly ask you to increase that time up to within 120 days after signing of contract.

Clarification No.4
We revise the time schedule of documentation's submitting as follows:

	Transformer drawings with all dimensions, aggregates, bushings location on tank, protection relays, measuring devices and secondary equipment for plant design   with all connection to tank and another transformer parts. Indicating also specification of weights: oil weight, active part weight, transport weight and weight of fully assembled transformer to the Purchaser’s approval- one copy of printed documentation and in an electronic form.
Secondary wiring diagrams, terminals diagrams, circuit diagrams of relay protection, cooling system and OLTC driver to the Purchaser’s approval.
	Within 90 days after signing of Contract

	Final production drawings for the Purchaser’s approval:  transformer drawings with all dimensions, aggregates, bushings location on tank, protection relays, measuring devices and secondary equipment for plant design with all connection to tank and another transformer parts. Indicating also specification of weights: oil weight, active part weight, transport weight and weight of fully assembled transformers to the finally Purchaser’s approval- two copies of printed documentation and in an electronic form.
Final secondary wiring diagrams, terminals diagrams, circuit diagrams of relay protection, cooling system and OLTC driver to the finally Purchaser’s approval.
	Within 120 days after signing of Contract




Tenderer's request for clarification No.5:
Please confirm that, payment schedule is; 30% before contract, 20% after signing contract, 30% after successful FAT, 10% after delivery, 10% after signing deed of transfer acceptance.

Clarification No.5
We cannot confirm the above-mentioned payment conditions. 

There is incorrect translation from Latvian to English in the Draft of agreement clause 4.4.3. (Annex No.5, page 74):
	[bookmark: _Hlk154587893]4.4.3.
	pēc Preces atvešanas uz Preču piegādes vietu un pēc transformatora uzstādīšanas uz pamatiem, ko apliecina Līguma 7.2.2.punktā minētā pieņemšanas – nodošanas akta abpusēja parakstīšana, Pasūtītājs veic maksājumu 90% apmērā no indeksētās Līguma cenas, atņemot no tās iepriekš izmaksāto avansa maksājumu, 30 (trīsdesmit) kalendāro dienu laikā pēc atbilstoša rēķina par piegādāto Preci no Piegādātāja saņemšanas;
	10% of the Contract price is paid within 30 (thirty) days after the completion of the transformer assembly work, performance of other related services, successful diagnostic results of the transformer (except for the tests mentioned in clauses 7.3 (m) and (n) of the Contract), which is confirmed by the deed of transfer-acceptance provided in Clause 7.2.3. of the Contract and signed by the Parties and submitting the invoice to the Purchaser;



With this we correct the translation from Latvian to English:
	4.4.3.
	pēc Preces atvešanas uz Preču piegādes vietu un pēc transformatora uzstādīšanas uz pamatiem, ko apliecina Līguma 7.2.2.punktā minētā pieņemšanas – nodošanas akta abpusēja parakstīšana, Pasūtītājs veic maksājumu 90% apmērā no indeksētās Līguma cenas, atņemot no tās iepriekš izmaksāto avansa maksājumu, 30 (trīsdesmit) kalendāro dienu laikā pēc atbilstoša rēķina par piegādāto Preci no Piegādātāja saņemšanas;
	Upon arrival of the Goods at the point of delivery and upon installation of the transformer on the foundations, as evidenced by the mutual signature of the deed of transfer-acceptance referred to in Clause 7.2.2 of the Agreement, the Purchaser shall pay 90% of the indexed Contract Price, less the advance payment previously made, within 30 (thirty) calendar days after receipt of the corresponding invoice for the Goods delivered from the Supplier;



The accurate description of the payment conditions (Draft of agreement, Annex No.5):

4.4. The Purchaser shall pay for the delivered Goods and the performed Services in the order indicated below:

4.4.1. upon the Supplier's request, the Purchaser shall make an Advance Payment of up to 20% of the Base Price (Cs) within 30 (thirty) calendar days after the mutual signature of the Contract, receipt of the Contract Performance Security and the Advance Payment Guarantee in accordance with the Contract (in the amount of the requested Advance Payment) and receipt of the corresponding Advance Invoice from the Supplier by transfer to the credit institution account specified in the Contract;

4.4.2. upon the Supplier's request, the Purchaser shall make an Advance Payment of up to 30% of the indexed Contract Price within 30 (thirty) calendar days after the FAT (factory tests) have been performed and submitted to the Purchaser, as evidenced by the mutual signature of the deed of transfer-acceptance referred to in Clause 7.2.1 of the Contract, receipt of the Advance Payment Guarantee (in the amount of the requested Advance Instalment) and receipt of the corresponding Advance Invoice from the Supplier by transfer to the credit institution account specified in the Contract;

4.4.3. Upon arrival of the Goods at the point of delivery and upon installation of the transformer on the foundations, as evidenced by the mutual signature of the deed of transfer-acceptance referred to in Clause 7.2.2 of the Agreement, the Purchaser shall pay 90% of the indexed Contract Price, less the advance payment previously made, within 30 (thirty) calendar days after receipt of the corresponding invoice for the Goods delivered from the Supplier;

4.4.4. upon completion of the assembly of the transformer, performance of other related services, successful results of diagnostics of the transformer (except for the tests referred to in Clause 7.3 (m) and (n) of the Contract) as evidenced by the mutual signature of the deed of transfer-acceptance referred to in Clause 7.2.3 of the Contract, the Purchaser shall make payment of 10% of the indexed Contract Price within 30 (thirty) calendar days after receipt of the relevant invoice from the Supplier.

Tenderer's request for clarification No.6:
In the first page of technical specifications following is mentioned, “No Load-Losses Po ≤ 10,5 kW”. Please revise that value. Requested value seems low as for the three-winding transformer, which usually are much bigger units.

Clarification No.6
We revise the technical specification's position
	Electric losses
	See below
	

	Minimum value of Peak Efficiency Index (PEI).
Considering guaranteed loss values.
	According to EU Commission Regulation EN 50629:2015 (table 1, column T2 (tier2))
	

	No-Load-Losses Po
	≤ 10,5 kW 
	



as follows:
	Electric losses
	See below
	

	Minimum value of Peak Efficiency Index (PEI).
Considering guaranteed loss values.
	According to EU Commission Regulation EN 50629:2015 (table 1, column T2 (tier2))
	

	No-Load-Losses Po
	≤ 12 kW 
	



Kind regards,
	Iepirkumu daļas vadītājs
	Kristīne Graudumniece





Juris Gavronskis
juris.gavronskis@ast.lv
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